## Gantt Chart Template
Group 15 GANTT CHART
| PROJECT TITLE | BookHive |  |  |  |  | TEAM | [8 empty] | Group 15
| GROUP NUMBER | 8 |  |  |  |  | DATE | [8 empty] | 2025-06-08
[7 empty] | MILESTONE ONE | [9 empty] | MILESTONE TWO | [9 empty] | MILESTONE THREE |  |  |  |  | MILESTONE FOUR | [9 empty] | MILESTONE FIVE |  |  |  |  | MILESTONE SIX | [9 empty] | MILESTONE SEVEN
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | PCT OF TASK COMPLETE | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6 |  |  |  |  | WEEK 7 |  |  |  |  | WEEK 8 |  |  |  |  | WEEK 9 |  |  |  |  | WEEK 10 |  |  |  |  | WEEK 11 |  |  |  |  | WEEK 12
[7 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
M1 | Requirement & Planning |  | Week 1 | Week 2 | 2 weeks
1.1 | Gather requirements |  | 2025-07-21 | 2025-07-31 | 9 | 100% | bar: WEEK 1 M to WEEK 1 F
1.2 | Team roles assigned and finalize MVP scope |  | 2025-07-21 | 2025-07-31 | 9 | 100% | bar: WEEK 2 M to WEEK 2 R
1.3 | SRS Draft & Review |  | 2025-07-21 | 2025-08-01 | 9 | 100% | bar: WEEK 2 M to WEEK 2 F
M2 | SRS & Design Finalized |  | Week 3 | Week 4 | 2 weeks
2.1 | Update MVP and Draft Requirements |  | 2025-08-04 | 2025-08-07 | 3 | 100% | bar: WEEK 3 M to WEEK 3 R
2.2 | Draw key UML diagrams (use case) |  | 2025-08-04 | 2025-08-07 | 3 | 100% | bar: WEEK 3 M to WEEK 3 R
2.3 | Complete wireframes for core flows (lending, borrowing) |  | 2025-08-04 | 2025-08-07 | 3 | 100% | bar: WEEK 3 M to WEEK 3 R
2.4 | Review & sign off architecture, design, and technical stack |  | 2025-08-04 | 2025-08-07 | 3 | 100% | bar: WEEK 3 M to WEEK 3 R
2.5 | Risk Management & Cost Evaluation |  | 2025-08-04 | 2025-08-07 | 3 | 100% | bar: WEEK 3 M to WEEK 3 R
2.6 | SRS Review & Lock (covering all Draft Requirements) |  | 2025-08-08 | 2025-08-14 | 6 | 100% | bar: WEEK 3 F to WEEK 4 F
M3 | Core Account & Profile System |  | Week 5 | Week 5 | 1 week
3.1 | Implement registration, login, email/OTP, password reset (FR01, FR02) |  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 5 R
3.2 | Login section-Frontend |  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 5 T
3.3 | Enforce security: encrypted password storage, HTTPS, rate limiting |  |  |  | 0 | 0% | bar: WEEK 5 M to WEEK 5 R
3.4 | Develop profile management (view/edit profile, upload photo, bio) |  |  |  | 0 | bar: WEEK 5 M to WEEK 5 F
3.5 | Set up blacklist and verification logic for users |  |  |  | 0 | 0% | bar: WEEK 5 F
M4 | Book & Lending Core Workflow MVP |  | Week 6 | Week 7 | 2 weeks
4.1 | Book CRUD: add/edit/delete/search/filter books |  |  |  | 0 | 0% | bar: WEEK 6 M to WEEK 7 M
4.2 | Implement lending workflow: approve/deny requests, manage book status |  |  |  | 0 | 0% | bar: WEEK 6 R to WEEK 7 F
4.3 | Borrowing workflow: request, approve, borrowing status tracking |  |  |  | 0 | 0% | bar: WEEK 6 F to WEEK 7 F
4.4 | Develop internal messaging & notification system |  |  |  | 0 | 0% | bar: WEEK 6 M to WEEK 7 M
M5 | Shipping/Payment/Fee Integration |  | Week 6 | Week 8 | 3 weeks
5.1 | Integrate shipping options: self-pickup, delivery, shipping fee estimation/management |  |  |  | 0 | 0% | bar: WEEK 8 M to WEEK 8 W
5.2 | Integrate payment gateway (e.g., Stripe): deposit collection, escrow, refund, compensation |  |  |  | 0 | 0% | bar: WEEK 8 M to WEEK 8 F
5.3 | Implement service fee configuration panel & fee deduction logic |  |  |  | 0 | 0% | bar: WEEK 8 M to WEEK 8 F
5.4 | Ensure all payment-related actions/status are visible to users |  |  |  | 0 | 0% | bar: WEEK 8 M to WEEK 8 F
M6 | Testing & Optimization |  | Week 9 | Week 10 | 2 weeks
6.1 | Implement feedback/review system, user statistics, transaction history |  |  |  | 0 | 0% | bar: WEEK 9 M to WEEK 10 F
6.2 | Complete all non-core features (comments, donation, affiliate link, etc.) |  |  |  | 0 | 0% | bar: WEEK 10 M to WEEK 10 F
6.3 | User, integration, and security testing; fix critical bugs |  |  |  | 0 | 0% | bar: WEEK 10 M to WEEK 10 F
6.1 | Deploy MVP for user acceptance testing |  |  |  | 0 | 0% | bar: WEEK 10 M to WEEK 10 F
M7 | Final Delivery |  | Week 10 | Week 11 | 2 weeks
7.1 | Complete all project documentation and deliverables |  |  |  | 0 | 0% | bar: WEEK 10 W to WEEK 11 F
7.2 | Prepare and present demo, poster, and final project report |  |  |  | 0 | 0% | bar: WEEK 11 M to WEEK 11 F